## Home
Team
Name |  |  | Number | Function
Manuel Fernandes |  |  | 23502 | Leader
João Cunha |  |  | 23519 | Secretary
Guilherme Azeredo |  |  | 23510 | Developer
Afonso Castro |  |  | 23513 | Developer
Meetings
Sprint #1 | Meet #1 | 2024-10-15
| Meet #2 | 2024-10-16
| Meet #3 | 2024-10-20

## Product Backlog
Product Backlog
ID | MoSCoW | As the user… | I want (to) … | Status
1
3
4
5
16
17
19
2
6
7
8
9
12
18
10
11
13
14
20
15
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Meet#1
ID | Status | Task | Who
1 | Done | Define roles for the project scructure | All
2 | Done | Gather ideas and details for the project | All
3 | Done | Contextualization of the project | All
4 | Done | Impact of this application | All
5 | Done | Write documentation | Manuel, Cunha
6 | Done | Requirements gathering | Manuel, Cunha
7 | Done | Diagram development | Cunha, Manuel
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Meet#2
ID | Status | Task | Who
1 | Done | Define internal regulamentation | Manuel, Cunha
2 | Done | Requirements gathering | All
3 | Done | Context Diagram development | Cunha, Manuel
4 | Done | BPMN Diagram Development | Cunha, Manuel
5 | Done | Explore possible features | All
6 | Done | Determine tools | All
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Meet#3
ID | Status | Task | Who
1 | Done | Define functional requisites | All
2 | Done | Define non functional requisites | All
3 | Done | Team meeting | All
4 | Done | Cronogram development | Manuel
5 | Done | Review of all previous documentation | All
6 | Done | Technical architecture of the application | Manuel, Cunha
7 | Done | Internal avaluation system | All
8 | Done | Viability Study | Manuel
9 | Done | Architecture Diagram | Cunha
10 | Done | Report | All
11 | Done | Stakeholders, description and business objectives | Azeredo
12
13
14
15
16
17
18
19
20
21
22
23
24
25